## Main Plan
ID | Section Number | Section Name | Primary Assignment | Primary Reviewer | V1 | V2 | Kanban | Inventory | Status as of 8/2
1 | 1 | Introduction | Jordan | Paul | 7/20 | 8/03 | Published Draft 2nd Pass | ASG_API Playbook_01.00 Introduction_Section_01.06_Published Draft Second Pass.docx
2 | 2.1 | Development Lifecyle | Max | Jordan | 6/15 | 7/27 | Published Draft 2nd Pass | ASG_API Playbook_02.01 Development Lifecycle_Section_01.08_Published Draft Second Pass.docx
3 | 2.2 | Industry Standards | Frank | Eric | 7/25 | 8/13 | SME Review Resolution | ASG_API_Playbook_02.02 Industry Standards_Section_01.02_Iniitial Draft {Frank Burgos}.docx
4 | 3 | API Layer | Jordan | Will/Eric | 7/15 | 8/03 | Published Draft 2nd Pass | ASG_API Playbook_03.00 API Layer_Section_01.06_Published Draft Second Pass.docx
5 | 4 | API Contracts | Max | Randhir | 6/30 | 8/13 | Tech Review | ASG_API Playbook_04.00 API Contracts_Section_01.03_SME Review Resolved {max.girin}.docx
6 | 5.1 | Naming Standards | Jordan | Max | 6/30 | 7/13 | Published Draft 2nd Pass | ASG_API Playbook_05.01 Naming Standards_Section_01.11_Published Draft Second Pass.docx
7 | 5.2 | Environment Properties | Jordan | Max | 7/15 | 8/03 | Deprecated?
8 | 5.3 | Configuration Parameters | Max | Will | 7/20 | 8/13 | Published Draft 2nd Pass | ASG_API Playbook_05.03 Configuration Parameters_01.07_Published Draft Second Pass.docx
9 | 5.4 | Objects and Methods | Max | Will | 8/03 | 8/20 | SME Review | ASG_API Playbook_05.04 Objects and Methods_Section_01.01_Initial Draft {max girin}.docx
10 | 5.5 | Middleware Artifacts | Max | Eric | 8/03 | 8/20 | SME Review Resolution | ASG_API Playbook_05.05 Middleware Artifacts_Section_01.01_Initial Draft {max girin}.docx
11 | 6 | Configuration Management | Frank | Max | 7/15 | 7/27 | Published Draft | ASG_API Playbook_06.00 Configuration Management_Section_01.07_Published Draft Second Pass.docx
12 | 7 | Unit Testing | Max | Frank | 7/15 | 8/20 | SME Review | ASG_API Playbook_07.00 Unit Testing_Section_01.03_SME Review Resolved {max.girin}.docx
13 | 8 | Developer Setup | Frank/Ron | Eric | 7/30 | 8/13 | SME Review Resolution | ASG_API Playbook_08.00 Developer Setup Section_02.01_SME Review Resolution {Frank Burgos}.docx | Ron to reach out to Frank
14 | 9.1 | Exception Handling Approach | Frank | Robert | 6/30 | 7/13 | Published Draft | ASG_API Playbook_09.01 Exception Handling_Section_01.11_Published Draft.docx
22 | 10 | Baseline Logging | Frank | Eric | 7/30 | 8/13 | SME Review Resolution | ASG_API Playbook_10.00 Baseline Logging_Section_01.03_SME_ Review Resolution {Frank Burgos}.docx
23 | 11 | Baseline API Security | Damien | John | 7/06 | 8/03 | VA Sensitive | ASG_API Playbook_11.00_Baseline Security_Section_01.01 VA Sensitive.docx
24 | 12.1 | What is a Re-usable Artifact | Dev | Max | 7/06 | 7/27 | SME Review | ASG_API Playbook_12.01_What is a Re-Usable Artifact_Section_01.01_Initial Draft {max.girin}.docx
25 | 12.2 | How to create Shared Components | Dev | Randhir | 7/27 | 8/13 | Published Draft | ASG_API Playbook_12.02 How To Create Shared Components_Section_01.04_Published Draft.docx
26 | 12.3 | Reuse Guidelines | Dev | Max | 7/06 | 7/27 | Published Draft | ASG_API Playbook_12.03 Reusability Section_01.07_Published Draft.docx
27 | 12.4 | Deploying Shared Components | Dev | Randhir | 7/27 | 8/13 | Published Draft | ASG_API Playbook_12.04 Deploying Shared Components_Section_01.04_Published Draft.docx
28 | 13 | API Documentation Blueprint | Eric | John | 7/27 | 8/13 | Tech Review | ASG_API Playbook_13.00 API Documentation Blueprint_Section_01.01_Initial Draft.docx

## Plan Compares
Section Name | Due Date | Old Section | Old Date | New Author Assignment | Old Assignment
Development Lifecyle | 6/15 | Deveopment Lifecylce | 6/15 | Max | Jordan
Introduction | 6/22 | Introduction | 6/22 | Jordan | Max
Exception Handling Approach | 6/30 | Exception Handling Approach | 7/30 | Frank | Jordan
Notification and Alerting | 6/30 | Notification and Alerting | 8/8 | Frank | Jordan
Middleware Level Exceptions | 6/30 | Middleware Level Exceptions | 9/10 | Frank | Max
Message Process Failures and Retries | 6/30 | Message Process Failures and Retries | 9/10 | Frank | Max
Exception Logging | 6/30 | Exception Logging | 9/10 | Frank | Max
Integration with Queuing | 6/30 | Integration with Queuing | 9/15 | Frank | Max
Global Exceptions | 6/30 | Global Exceptions | 8/31 | Frank | Max
API Level Exceptions | 6/30 | API Level Exceptions | 8/31 | Frank | Max
Naming Standards | 6/30 | Naming Standards | 7/15 | Jordan | Jordan
API Contracts | 6/30 | API Layer | 6/30 | Max | Jordan
Developer Setup | 7/06 | API Contracts | 6/30 | Ron | Max
Baseline API Security | 7/06 | Developer Setup | 8/31 | Damien | Max
API Documentation Blueprint | 7/06 | Baseline API Security | TBD | Eric | Max
What is a Re-usable Artifact | 7/06 | API Documentation Blueprint | TBD | Dev | Jordan
Reuse Guidelines | 7/06 | What is a Re-usable Artifact | 8/17 | Dev | Jordan
How to create Shared Components | 7/06 | Reuse Guidelines | 8/31 | Dev | Jordan
Deploying Shared Components | 7/06 | How to create Shared Components | 9/30 | Dev | Max
API Layer | 7/15 | Deploying Shared Components | 9/30 | Jordan | Max
Environment Properties | 7/15 | Environment Properties | 7/15 | Max | Max
Configuration Parameters | 7/15 | Configuration Parameters | 7/15 | Max | Max
Objects and Methods | 7/15 | Objects and Methods | 7/15 | Max | Max
Unit Testing | 7/15 | Unit Testing | 8/17 | Max | Max
Configuration Management | 7/15 | Configuration Management | 8/03 | Frank | Max
Middleware Artifacts | 7/22 | Middleware Artifacts | 7/22 | Max | Max
Baseline Logging | 7/30 | Baseline Logging | 9/21 | Frank | Max
Industry Standards | 8/15 | Industry Standards | 7/30 | Frank | Jordan