## Sheet1
ID | Section Number | Section Name | Assignment | Due Date | Notes
1 | 1 | Introduction | Jordan | 6/22
2 | 2.1 | Development Lifecyle | Max | 6/15
3 | 2.2 | Industry Standards | Jordan | 7/30
4 | 3 | API Layer | Jordan | 6/30
5 | 4 | API Contracts | Max | 6/30
6 | 5.1 | Naming Standards | Jordan | 7/15
7 | 5.2 | Environment Properties | Max | 7/15
8 | 5.3 | Configuration Parameters | Max | 7/15
9 | 5.4 | Objects and Methods | Max | 7/15
10 | 5.5 | Middleware Artifacts | Max | 7/22
11 | 6 | Configuration Management | Max | 8/03
12 | 7 | Unit Testing | Max | 8/17
13 | 8 | Developer Setup | Max | 8/31
14 | 9.1 | Exception Handling Approach | Jordan | 7/30
15 | 9.2 | Global Exceptions | Max | 8/31
16 | 9.3 | API Level Exceptions | Max | 8/31
17 | 9.4 | Middleware Level Exceptions | Max | 9/10
18 | 9.5 | Message Process Failures and Retries | Max | 9/10
19 | 9.6 | Exception Logging | Max | 9/10
20 | 9.7 | Notification and Alerting | Jordan | 8/8
21 | 9.8 | Integration with Queuing | Max | 9/15
22 | 10 | Baseline Logging | Max | 9/21
23 | 11 | Baseline API Security | Max | TBD | Awaiting Analysis of API Working Group Design Patterns
24 | 12.1 | What is a Re-usable Artifact | Jordan | 8/17
25 | 12.2 | How to create Shared Components | Max | 9/30
26 | 12.3 | Reuse Guidelines | Jordan | 8/31
27 | 12.4 | Deploying Shared Components | Max | 9/30
28 | 13 | API Documentation Blueprint | Jordan | TBD