## Main Plan
ID | Section Number | Section Name | Primary Assignment | Primary Reviewer | V1 | V2 | Arch Review (Jordan) | Editing Review (Paul) | Status as of 7/27
2 | 2.1 | Development Lifecyle | Max | Jordan | 6/15 | 7/27 |  |  | Ready for final review.
5 | 4 | API Contracts | Max | Randhir | 6/30 | 8/13 |  |  | Reviewed and Feedback received. V2 in progress.
6 | 5.1 | Naming Standards | Jordan | John | 6/30 | 7/13 | Completed |  | Submitted to VA for review.
14 | 9.1 | Exception Handling Approach | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
15 | 9.2 | Global Exceptions | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
16 | 9.3 | API Level Exceptions | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
17 | 9.4 | Middleware Level Exceptions | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
18 | 9.5 | Message Process Failures and Retries | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
19 | 9.6 | Exception Logging | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
20 | 9.7 | Notification and Alerting | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
21 | 9.8 | Integration with Queuing | Frank | Robert | 6/30 | 7/13 | 7/31 |  | Ready for final review.
23 | 11 | Baseline API Security | Damien | John | 7/06 | 8/03 |  |  | V1 Draft received. Review in Progress
24 | 12.1 | What is a Re-usable Artifact | Dev | Max | 7/06 | 7/27 |  |  | Review Completed. V2 In Progress
26 | 12.3 | Reuse Guidelines | Dev | Max | 7/06 | 7/27 |  |  | Review Completed. V2 In Progress
4 | 3 | API Layer | Jordan | Will/Eric | 7/15 | 8/03 |  |  | V1 Draft Received. Review In Progress
7 | 5.2 | Environment Properties | Jordan | Max | 7/15 | 8/03 |  |  | Reviewed and Feedback provided. V2 In Progress.
11 | 6 | Configuration Management | Frank | Max | 7/15 | 7/27 |  |  | Reviewed and Feedback received. V2 in progress.
12 | 7 | Unit Testing | Max | Frank | 7/15 | 8/20 |  |  | V1 Draft received. Review not started.
1 | 1 | Introduction | Jordan | Paul | 7/20 | 8/03 |  |  | V1 Draft Received. Review In Progress
8 | 5.3 | Configuration Parameters | Max | Will | 7/20 | 8/13 |  |  | V1 Draft received. Review not started.
3 | 2.2 | Industry Standards | Frank | Eric | 7/25 | 8/13 |  |  | V1 Draft received. Review not started.
25 | 12.2 | How to create Shared Components | Dev | Randhir | 7/27 | 8/13 |  |  | V1 In Progress.
27 | 12.4 | Deploying Shared Components | Dev | Randhir | 7/27 | 8/13 |  |  | V1 In Progress.
28 | 13 | API Documentation Blueprint | Eric | John | 7/27 | 8/13 |  |  | V1 Draft received. Review not started.
13 | 8 | Developer Setup | Frank | Eric | 7/30 | 8/13
22 | 10 | Baseline Logging | Frank | Eric | 7/30 | 8/13 |  |  | V1 Draft received. Review not started.
9 | 5.4 | Objects and Methods | Max | Will | 8/03 | 8/20 |  |  | V1 In progress
10 | 5.5 | Middleware Artifacts | Max | Eric | 8/03 | 8/20 |  |  | V1 In Progress

## Plan Compares
Section Name | Due Date | Old Section | Old Date | New Author Assignment | Old Assignment
Development Lifecyle | 6/15 | Deveopment Lifecylce | 6/15 | Max | Jordan
Introduction | 6/22 | Introduction | 6/22 | Jordan | Max
Exception Handling Approach | 6/30 | Exception Handling Approach | 7/30 | Frank | Jordan
Notification and Alerting | 6/30 | Notification and Alerting | 8/8 | Frank | Jordan
Middleware Level Exceptions | 6/30 | Middleware Level Exceptions | 9/10 | Frank | Max
Message Process Failures and Retries | 6/30 | Message Process Failures and Retries | 9/10 | Frank | Max
Exception Logging | 6/30 | Exception Logging | 9/10 | Frank | Max
Integration with Queuing | 6/30 | Integration with Queuing | 9/15 | Frank | Max
Global Exceptions | 6/30 | Global Exceptions | 8/31 | Frank | Max
API Level Exceptions | 6/30 | API Level Exceptions | 8/31 | Frank | Max
Naming Standards | 6/30 | Naming Standards | 7/15 | Jordan | Jordan
API Contracts | 6/30 | API Layer | 6/30 | Max | Jordan
Developer Setup | 7/06 | API Contracts | 6/30 | Ron | Max
Baseline API Security | 7/06 | Developer Setup | 8/31 | Damien | Max
API Documentation Blueprint | 7/06 | Baseline API Security | TBD | Eric | Max
What is a Re-usable Artifact | 7/06 | API Documentation Blueprint | TBD | Dev | Jordan
Reuse Guidelines | 7/06 | What is a Re-usable Artifact | 8/17 | Dev | Jordan
How to create Shared Components | 7/06 | Reuse Guidelines | 8/31 | Dev | Jordan
Deploying Shared Components | 7/06 | How to create Shared Components | 9/30 | Dev | Max
API Layer | 7/15 | Deploying Shared Components | 9/30 | Jordan | Max
Environment Properties | 7/15 | Environment Properties | 7/15 | Max | Max
Configuration Parameters | 7/15 | Configuration Parameters | 7/15 | Max | Max
Objects and Methods | 7/15 | Objects and Methods | 7/15 | Max | Max
Unit Testing | 7/15 | Unit Testing | 8/17 | Max | Max
Configuration Management | 7/15 | Configuration Management | 8/03 | Frank | Max
Middleware Artifacts | 7/22 | Middleware Artifacts | 7/22 | Max | Max
Baseline Logging | 7/30 | Baseline Logging | 9/21 | Frank | Max
Industry Standards | 8/15 | Industry Standards | 7/30 | Frank | Jordan